## Sheet1
Test Case ID | Reviewer | Author Name | Review Date | Finding | Severity | Recommendation | Author comment | Fixed VersionStatus | Document Version
InfoSys_DualButton_MuteOnOff_001 | Mahmoud ABDELHAMID | Andrew MESSIHA | 2023-12-27 | To provide a consistent and dependable test environment, the author should explicitly specify the requirements needed for the test case, such as the infotainment system's current state and the buttons' operation. | Major | To provide a consistent and dependable test environment, the author should explicitly specify the requirements needed for the test case, such as the infotainment system's current state and the buttons' operation. | Acknowledged. Will specify test case requirements, including infotainment system state and button operations, in the next document version. | In Progress | 1.1
InfoSys_DualButton_Mute_002 | Farida GHARIB | George WASEEM | 2023-12-27 | The desired behavior of the system in response to the duration of the button press is not thoroughly described in the test case. It should specify the precise expected system reactions for various button press times for the Mute signal. | Major | The intended system reactions for various button press durations connected to the Mute signal should be clearly and completely described by the author. This will guarantee that the button's functioning is accurately assessed by the test case. | Acknowledged. Will be updated in the next document version. | In Progress | 1.1
InfoSys_DualButton_OnOff_003 | Mahmoud ABDELHAMID | Andrew MESSIHA | 2023-12-27 | The desired behavior of the system in response to the duration of the button press is not thoroughly described in the test case. It should specify the precise expected system reactions for various button press times for the On/Off signal. | Minor | Regarding the On/Off signal, the author should include a concise and comprehensive explanation of the expected system responses for various button press durations. This will guarantee that the button's functioning is accurately assessed by the test case. | Acknowledged. Will be updated in the next document version. | In Progress | 1.1
InfoSys_Button_Stuck_007 | Mahmoud ABDELHAMID | Andrew MESSIHA | 2023-12-27 | The test case does not provide a thorough explanation of how the system should react in the event that a button becomes stuck. It ought to outline precise expected system reactions in the event that a button becomes stuck. | Minor | The test case should guarantee that the system keeps working correctly for operations unaffected by the stuck button and that the user receives useful notifications about the stuck button condition and the associated DTC codes. | Acknowledged. Will be updated in the next document version. | In Progress | 1.1
InfoSys_ButtonDTC_Stuck_008 | Farida GHARIB | George WASEEM | 2023-12-27 | There are no explicit procedures in the test case InfoSys_ButtonDTC_Stuck_008 to confirm that the DTC codes are correctly cleared when the stuck button issue is fixed. | Minor | In order to ensure that the system properly clears the DTC codes when the stuck button issue is fixed, the author should provide detailed instructions. The expected system behavior after the stuck button issue is fixed, including the precise steps the system should follow and the associated DTC codes that need to be cleared, should be clearly outlined in the results section. | Feedback received. The upcoming document version will contain explicit requirements for the test case. | In Progress | 1.1
InfoSys_Button_SIGMute_004 | George WASEEM | Farida GHARIB | 2023-12-27 | The test case should make sure that the system keeps working normally for operations unaffected by the activation of the mute signal and that the user receives informative signals about the system's reaction to the activation of the mute signal. | Minor | The author should specify how to confirm that the system is functioning normally and that other system responses have not been impacted by the silence signal's functionality. | Understood. Detailed specifications for the test environment will be included in the next version. | In Progress | 1.1
InfoSys_Button_SIGOnOff_005 | George WASEEM | Andrew MESSIHA | 2023-12-27 | The test case should make sure that the system keeps working correctly for functions that are unaffected by the manipulation of the onoff_state signal and that the user receives informative signals about how the system reacts to the manipulation of the onoff_state signal. | Minor | The author should specify how to confirm that the system is operating normally and that other system responses have not been impacted by the onoff signal's functionality. | Understood. Detailed specifications for the test environment will be included in the next version. | In Progress | 1.1
InfoSys_Ign_UserStateSaving_006 | Farida GHARIB | Farida GHARIB | 2023-12-27 | N/A | N/A | N/A | N/A | N/A | N/A
InfoSys_InputSignal_LossHandle_009 | George WASEEM | Mahmoud ABDELHAMID | 2023-12-27 | There are no explicit steps in the test case to confirm that the DTC codes are correctly cleared after the stuck button issue is fixed. | Minor | In order to ensure that the system properly clears the DTC codes when the stuck button issue is fixed, the author should provide detailed instructions. The expected system behavior after the stuck button issue is fixed, including the precise steps the system should follow and the associated DTC codes that need to be cleared, should be clearly outlined in the results section. | Acknowledged. Will be updated in the next document version. | Open | 1.1
InfoSys_BacklightStatus_DayNight_010 | Farida GHARIB | Mahmoud ABDELHAMID | 2023-12-27 | The test case should make sure that the system keeps working regularly for functions unaffected by the Day_Night signal change and that the user receives informative messages about how the system reacts to the activation of the mute signal. | Minor | To ensure that the system is functioning normally and that other system responses have not been impacted by the Day_Night signal's functionality, the author should provide precise instructions. | Acknowledged. Will be updated in the next document version. | Open | 1.1
InfoSys_BacklightPWM_Day_011 | Farida GHARIB | Andrew MESSIHA | 2023-12-27 | N/A | N/A | N/A | N/A | N/A | N/A
InfoSys_BacklightPWM_Night_012 | Andrew MESSIHA | George WASEEM | 2023-12-27 | N/A | N/A | N/A | N/A | N/A | N/A
InfoSys_diagnosticParameters_Push_013 | Andrew MESSIHA | George WASEEM | 2023-12-28 | The test case does not guarantee that the user receives informative notifications about the system's response to parameter configuration, nor does it guarantee that the system keeps functioning normally for functions that are unaffected by the setup of the push's durational parameters. | Minor | The author ought to outline precise procedures for confirming that the system functions normally and that setting such durations hasn't had an impact on other system responses. | Acknowledged. Will be updated in the next document version. | Open | 1.1
InfoSys_diagnosticParameters_DayNight_014 | George WASEEM | Farida GHARIB | 2023-12-28 | The test case does not guarantee that the system will continue to function normally for functions that are unaffected by the diagnostic services' configuration of the duty cycle parameters during the day and that the user will receive informative messages about the system's response to the parameter configuration. | Minor | The author must to outline precise procedures for confirming that setting up these settings hasn't had an impact on other system responses and that the system is functioning normally. | Acknowledged. Will be updated in the next document version. | Open | 1.1
InfoSys_ConfigParameters_SysRestart_015 | Farida GHARIB | Mahmoud ABDELHAMID | 2023-12-28 | The test case does not guarantee that the user receives informative messages about the system's response to parameter configuration, nor does it guarantee that the system keeps functioning correctly for functions that are unaffected by parameter configuration. | Minor | To ensure that setting these settings hasn't impacted other system responses and that the system is functioning normally, the author should provide detailed instructions. | Acknowledged. Will be updated in the next document version. | Open | N/A
infoSys_DID0203_RDBI_016 | Mahmoud ABDELHAMID | George WASEEM | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0203_WDBI_018 | Farida GHARIB | Andrew MESSIHA | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0203_IncorrectFormat_019 | Farida GHARIB | George WASEEM | 2023-12-28 | The format of the wrong data to be utilized in testing the Write Data By Identifier (WDBI) service for DID 0203 is not specified in the test case. Replicating the test scenario may become challenging as a result, and testing results may become inconsistent. | Minor | To test the WDBI service for DID 0203, the test case has to outline the precise format of the erroneous data. This will facilitate the test case's replication and aid to maintain consistency throughout the testing procedure. | Acknowledged. Will be updated in the next document version. | Open | 1.1
infoSys_DID0203_SetTSHORTLONG_022 | Mahmoud ABDELHAMID | George WASEEM | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0203_SetTDAYNIGHTDC_023 | Andrew MESSIHA | Mahmoud ABDELHAMID | 2023-12-28 | The test case does not indicate the range of Day_DC and Night_DC acceptable values. This might cause testing findings to be inconsistent, making it challenging to assess whether the system is operating appropriately. | Minor | The range of acceptable values for Day DC and Night DC should be specified in the test case. This will facilitate the process of ensuring uniformity in the testing procedure and facilitate the assessment of the system's functionality. | Acknowledged. Will be updated in the next document version. | Open | 1.1
infoSys_DID0204_RDBI_017 | George WASEEM | Andrew MESSIHA | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0204_WDBI_019 | George WASEEM | Mahmoud ABDELHAMID | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0204_WDBISercuity_018 | Andrew MESSIHA | Farida GHARIB | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_DID0204_IncorrectFormat_020 | Farida GHARIB | Andrew MESSIHA | 2023-12-28 | The format of the wrong data to be utilized in testing the Write Data By Identifier (WDBI) service for DID 0204 is not specified in the test case. Replicating the test scenario may become challenging as a result, and testing results may become inconsistent. | Minor | When testing the WDBI service for DID 0204, the test case should outline the precise format of the erroneous data. This will facilitate the test case's replication and aid to maintain consistency throughout the testing procedure. | Acknowledged. Will be updated in the next document version. | Open | 1.1
infoSys_Diagnostics_WrongService_021 | Farida GHARIB | Mahmoud ABDELHAMID | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A
infoSys_IOCBI0205_BacklightControl_024 | Mahmoud ABDELHAMID | Andrew MESSIHA | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A