## Test Collection
Test Case | Reviewed By | Author | Result | Expected Result | Actual Result | Failed Reason | Date | SW | Defect ID | Comment
InfoSys_DualButton_MuteOnOff_001 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | InfoSys system status should be ON InfoSys Mute status should be Mute | InfoSys system status Is OFF InfoSys mute status is UnMute | The Time for (T_SHORT, T_LONG) for is configured incorrectly for T_SHORT: at range 4000ms till 4999 ms for T_LONG: at range 5000ms till 29999 ms | Thu Dec 28 16:18:28 EET 2023 | 4b4335b - last commit from github | DEF-101 | N/A
InfoSys_DualButton_Mute_002 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. InfoSys Mute Status at 750ms should be Unmute 2. InfoSys Mute Status at 800ms should be Mute 3. InfoSys Mute Status at 850ms should be Mute | 1. InfoSys Mute Status at 750ms is Unmute 2. InfoSys Mute Status at 800ms is Unmute 3. InfoSys Mute Status at 850ms is Unmute | The Time for (T_SHORT) for Mute option is configured incorrectly at range 4000ms till 4999 ms | Thu Dec 28 16:41:15 EET 2023 | 4b4335b - last commit from github | DEF- 102 | N/A
InfoSys_DualButton_OnOff_003 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. InfoSys On/Off Status at 1750ms should be OFF 2. InfoSys On/Off Status at 1800ms should be ON 3. InfoSys On/Off Status at 1850ms should be ON | 1. InfoSys On/Off Status at 1750ms is OFF 2. InfoSys On/Off Status at 1800ms is OFF 3. InfoSys On/Off Status at 1850ms is OFF | The Timer for (T_LONG) On/Off option is configured incorrectly at range at 5000ms till 29999ms | Thu Dec 28 16:41:15 EET 2023 | 4b4335b - last commit from github | DEF- 103 | N/A
InfoSys_Button_Stuck_007 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. InfoSys Button Stuck Status at 59750ms should be Unstucked 2. InfoSys Button Stuck Status at 59800ms should be Stucked 3. InfoSys Button Stuck Status at 59850ms should be Stucked | 1. InfoSys Button Stuck Status at 59750ms is Stucked 2. InfoSys Button Stuck Status at 59800ms is Stucked 3. InfoSys Button Stuck Status at 59850ms is Stucked | The Timer for the button to be stucked is configured incorrectly at 30000ms | Thu Dec 28 16:41:15 EET 2023 | 4b4335b - last commit from github | DEF- 104 | N/A
InfoSys_ButtonDTC_Stuck_008 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. InfoSys Button Stuck Status at 59750ms should be Unstucked and DTC should return B91212: 0x0 (NO_ISSUE) 2. InfoSys Button Stuck Status at 59800ms should be Stucked and DTC should return B91212: 0x9 (CONFIRMED_AND_FAILED) 3. InfoSys Button Stuck Status at 59850ms should be Stucked and DTC should return B91212: 0x9 4. InfoSys Button Remove Stuck After 2000ms should be considerd Unstucked and DTC should return B91212: 0x8(CONFIRMED) | 1. InfoSys Button Stuck Status at 59750ms is Stucked and DTC returned B91212: 0x9 2. InfoSys Button Stuck Status at 59800ms is Stucked and DTC returned B91212: 0x9 3. InfoSys Button Stuck Status at 59850ms is Stucked and DTC returned B91212: 0x9 4. InfoSys Button Remove Stuck After 2000ms is Unstucked and DTC returned B91212: 0x8 | The Timer for the button to be stucked is configured incorrectly at 30000ms, Therefore at all timing the button is already considerd to be stuck | Tue Dec 26 20:45:28 EET 2023 | 4b4335b - last commit from github | DEF- 201 | N/A
InfoSys_Ign_UserStateSaving_006 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. InfoSys Mute Status at 850ms should be Mute , After Turning the IGN off then On The last Saved Mute Status should be Mute 2. InfoSys On/Off Status at 1850ms should be ON , After Turning the IGN off then On The Last Saved On/Off Status should be ON | After Turning the Ign Off then On 1. InfoSys Mute Status at 850ms is Unmute , Last Saved Mute status is Unmute 2. InfoSys On/Off Status at 1850ms is OFF , Last Saved On/Off status is OFF | The Timing for (T_SHORT, T_LONG) is configured incorrectly, Therefore, Mute and On/off status won't get updated | Wed Dec 27 19:12:48 EET 2023 | 4b4335b - last commit from github | DEF- 301 | N/A
InfoSys_BacklightPWM_Day_011 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. At Day, Backlight Duty Cycle is expected to be 39.2 2. At Night, Backlight Duty Cycle is expected to be 78.4 | 1. At Day, Backlight Duty Cycle is 78.4 2. At Night, Backlight Duty Cycle is 39.2 | The Configuration of PWM of Day/Night is inverted | Thu Dec 28 01:06:32 EET 2023 | 4b4335b - last commit from github | DEF- 401 | This test case includes a deviation due to a known bug DEF-103). The on/off button is pressed for 6000ms instead of the required 2000ms to turn the system on. This workaround enables testing of the backlight functionality. The test case will be updated once the bug is fixed.
InfoSys_diagnosticParameters_Push_013 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. After diagonstic parameter configure (T_SHORT) to be 1500ms , InfoSys Mute Status at 1500ms should be Mute 2. After After diagonstic parameter configure (T_LONG) to be 2500ms , InfoSys On/Off Status at 2500ms should be Off | 1. InfoSys Mute Status at 1500ms is Unmute 2. InfoSys On/Off Status at 2500ms is Off | The Configuration Dignostics Parameter for T_Short, T_long does not get set to the desired values (1500,2500) | Thu Dec 28 02:17:57 EET 2023 | 4b4335b - last commit from github | DEF- 501 | N/A
InfoSys_diagnosticParameters_DayNight_014 | Mahmoud Abdelhamid | Andrew MESSIHA | Pass | 1. After Configure Day_DC to be 70% , Backlight Duty Cycle should be 70.0 2. After Configure Night_DC to be 30% , Backlight Duty Cycle should be 30.0 | 1. At Day, Backlight Duty Cycle is 70.0 2. At Night, Backlight Duty Cycle is 30.0 | N/A | Thu Dec 28 02:17:57 EET 2023 | 4b4335b - last commit from github | NONE | This test case includes a deviation due to a known bug DEF-103). The on/off button is pressed for 6000ms instead of the required 2000ms to turn the system on. This workaround enables testing of the backlight functionality. The test case will be updated once the bug is fixed.
InfoSys_ConfigParameters_SysRestart_015 | Mahmoud Abdelhamid | Andrew MESSIHA | NOK | 1. After diagonstic parameter Configure t_short to be 1500ms , InfoSys Mute Status at 1500ms should be Mute 2. After diagonstic parameter Configure t_long to be 2500ms , InfoSys On/Off Status at 2500ms should be Off 3. After Configure Day_DC to be 70% , Backlight Duty Cycle should be 70.0 4. After Configure Night_DC to be 30% , Backlight Duty Cycle should be 30.0 | 1. InfoSys Mute Status at 1500ms is Unmute 2. InfoSys On/Off Status at 2500ms is Off 3. At Day, Backlight Duty Cycle is 70.0 4. At Night, Backlight Duty Cycle is 30.0 | The Timing for (T_SHORT, T_LONG) is configured incorrectly, Therefore, Mute and On/off status won't get updated | Thu Dec 28 02:17:57 EET 2023 | 4b4335b - last commit from github | DEF-502 | This test case includes a deviation due to a known bug DEF-103). The on/off button is pressed for 6000ms instead of the required 2000ms to turn the system on. This workaround enables testing of the backlight functionality. The test case will be updated once the bug is fixed.

## Defect Log
Defect ID | Defect Description | Evidence | Status | Defect Root | Refrenece Defect
DEF-101 | In time 1000ms: Expected: the Mute status should be mute Actual: the infosys is unmuted | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for Mute status is configured at 4000ms till 4999ms , it should be 1000ms till 1999ms | N/A
DEF-101 | In time 2000ms : Expected: the On/Off status should be ON Actual: the infosys system status is OFF | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for On/Off statue is configured at 5000ms till 29999ms , it should be 2000ms till 5999ms (T_Long) | N/A
DEF-102 | In time 800ms: Expected: the Mute status should be mute Actual: the infosys is unmuted | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for Mute status is configured at 4000ms till 4999ms , it should be 1000ms till 1999ms | N/A
DEF- 102 | In time 850ms: Expected: the Mute status should be mute Actual: the infosys is unmuted | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for Mute status is configured at 4000ms till 4999ms , it should be 1000ms till 1999ms (T_Short) | N/A
DEF- 103 | In time 1800ms : Expected: the On/Off status should be on Actual: the infosys system status is Off | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for On/Off statue is configured at 5000ms till 29999ms , it should be 2000ms till 5999ms (T_Long) | N/A
DEF- 103 | In time 1850ms : Expected: the On/Off status should be on Actual: the infosys system status is Off | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for On/Off statue is configured at 5000ms till 29999ms , it should be 2000ms till 5999ms (T_Long) | N/A
DEF- 104 | In time 59750ms: Expected: the Button should be unstucked Actual: the infosys is stucked | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for Stucking is configured at 30000ms , it should be 60000ms | N/A
DEF- 201 | In time 59750ms: Expected: the Button should be unstucked and the DTC should return B91212: 0x0 Actual: the infosys is stucked and DTC returend B91212: 0x9 | #VALUE! | In Progress | In the configuration of the InfoSys's system the timer for Stucking is configured at 30000ms , it should be 60000ms In the configuration of the InfoSys’s DTC is should return B91212: 0x0 | N/A
DEF- 301 | In time 850ms the Mute status should be mute so after turning the IGN Off then On. The Last Saved Mute Status should be Mute Actual: the InfoSys is Unmuted and The Last Saved Mute Status is Unmuted | #VALUE! | In Progress | This defect is caused by the infosys system status being OFF, So to bypass this we must update the system status to ON by pressing the on_off button (6000ms), after that step this defect will be resolved. | DEF- 101/DEF- 103
DEF- 401 | At Day , Backlight Duty Cycle should be equal 39.2 as per the equation of the Duty Cycle [(PWM/255)*100] as the PWM of Day = 100 . The Acutal Result of the test case Backlight Duty Cycle is 78.4 | #VALUE! | In Progress | In the configuration of the InfoSys's Dignostics for the Day/Night PWM , Day's PWM = 200 while Night's PWM = 100 these 2 values are inverted. The right values should be Day's PWM = 100 while Night's PWM = 200 | DEF- 101/DEF- 103
DEF- 401 | At Night , Backlight Duty Cycle should be equal 78.4 as per the equation of the Duty Cycle [(PWM/255)*100] as the PWM of Night = 200 . The Acutal Result of the test case Backlight Duty Cycle is 39.2 | #VALUE! | In Progress | In the configuration of the InfoSys's Dignostics for the Day/Night PWM , Day's PWM = 200 while Night's PWM = 100 these 2 values are inverted. The right values should be Day's PWM = 100 while Night's PWM = 200 | DEF- 101/DEF- 103
DEF- 501 | After Configure T_Short to be 1500ms AND Restarting the System , InfoSys Mute Status at 1500ms should be Mute but the Actual Result was Unmute | #VALUE! | In Progress | The Configuration Dignostics Parameter for T_Short does not update the parameter to the desired value 1500ms after Restarting the system | N/A
DEF- 502 | After Configure T_Short to be 1500ms AND Restarting the system , InfoSys Mute Status at 1500ms should be Mute but the Actual Result was Unmute | #VALUE! | In Progress | The Configuration Dignostics Parameter for T_Short does not update the parameter to the desired value 1500ms after Restarting the system | DEF - 501